## Sheet3
Red - Need explanations
Phase II |  | Priority | Comments | Additional Information | Delivery Prioritization | Hours
1 | Mobile Application (Web App) | High (Required Immediately)
2 | Issues: | NA
2.1 | Performance Issue: | NA
2.2 | Issue: After Registration / Order | High (Required Immediately) | 1. After the User registration is done need go back to the Sign on screen 2. After the vendor registration is done need to go back to the sign screen and also there should be a message that the registration under review some one from Lyklyst would get back to you shortly (Pop up message) 3. Once the order is placed by Wallet or Payment gateway we need to should a message with the order number if it was places successfully or failed ( Show invoice and payment status) | Refer | 1 | 6
2.3 | Issue with Status: Delivery Status & Payment Status missing when the delivery is completed | High (Required Immediately) | Check the screen shot | Refer | 2 | 4
2.4 | Google Maps are not loading | High (Required Immediately) | No new development required, need to generate key and assign it in Control Panel |  |  | 1
3 | Terms & Conditions | Low
3.1 | Separate Terms & Condition / Privacy Policy for Vendor | Low |  |  |  | 6
3.2 | Separate Terms & Condition / Privacy Policy for Customers | Low |  |  |  | 3
4 | Activate Captcha | Low
4.1 | Activate Captcha for Customer Login / Vendor Login / Admin Login | Low |  |  |  | 2
4.2 | Activate Captcha for User Registration | NA
4.3 | Contact us | NA
4.4. | Vendor Registration | NA
5 | UI Related | NA
5.1 | Add Links to Mobile Application – from Admin Control Panel | High (Required Immediately) | Need a UI to upload Links / Images to the lyklyst mobile apps in different marketplace and stores | Refer |  | 5
5.2 | Social Links in Admin & Micro Sites | High (Required Immediately) |  |  |  | 2
5.2.1 | Remove G+ | High (Required Immediately)
5.2.2 | Add Instagram | High (Required Immediately)
5.2.3 | Add WhatsApp | High (Required Immediately)
5.2.4 | Add Telegram | High (Required Immediately)
5.3 | Message Box ( for Admin UI and Admin control Panel) | High (Required Immediately) | Need a UI in the Control Panel to update the Header in the message box, wysiwyg editor required | Refer |  | 7
5.4 | Footer Logo ( Vendor & Admin) | High (Required Immediately) | Need a UI in the Control Panel wysiwyg editor | Refer |  | 6
5.5 | Add Footer (Our Information) - Vendor & Admin | High (Required Immediately) | Need a UI in the Control Panel wysiwyg editor | Refer |  | 4
5.6 | Add footer band - Admin | High (Required Immediately) | Need a UI in the Control Panel wysiwyg editor | Refer |  | 4
5.7 | Add vendor name in the Shopping Cart | Medium | in which pages? - Shopping cart launched from Global / Vendor site | Refer |  | 2
6 | Product Details screen | Medium | Add featured product block before related products | Refer |  | 3
7 | Share on Social Media (Product Card / Product Detailed Screen / Blog / Events) | High (Required Immediately) | Need the social media lists; Facebook, Instagram, Twitter, Linkedin, Whatsapp, Telegram, Skype; Need on Product Card / Product Detailed Screen / Blog / Events |  |  | 5
7.1 | Share option in product detailed screen | Medium |  |  |  | 2
7.2 | Share option on Card | Medium |  |  |  | 4
8 | Product Post on Social media ( @ Product Page / Event & Blog) Social Media of Lyklyst & Social media of vendor ) | Medium | Need to Post information Product / Event / Blog / by the Admin and Vendor, in all social media. Need to develop UI |  |  | Need time to analyz
9 | Session Time out | Medium | Currently if user log into the Control panel, the session remain active for ever. So once logged in and if there is an inactivity form user to for 5 mins then the session should expire, this time setting needs to be controlled from the Admin Panel |  |  | 3
10 | Detect User Location | High (Required Immediately) | When any user log on to Site (Global / Vendor site) the location and pin code should be automatically updated and store in cookies When User login to the site just look for location access in browser / device, if no access then it should show as • Deliver to --- • Location ----- Pick up the correct location when he login into customer account |  |  | 4
11 | Add New Category Table | Medium | Need a separate table to created for adding Vendor Category & Blog Category (Just like product category and sub category) |  |  | 16
12 | Vendor / Profiles | NA
12.1 | Required Detailed Screen | Medium | Need a detailed Screen to edit vendor details | Refer |  | 4
12.2 | Activating and Deactivating in Vendor Site | NA
12.2.1 | Store Locator | High (Required Immediately) | Need option to enable and disable Store locator page from the Admin Control Panel ( Profile >> Profile List Page ) |  |  | 2
12.2.2 | Contact us | High (Required Immediately) | Need option to enable and disable Contact us page from the Admin Control Panel ( Profile >> Profile List Page ) Disable Address in Contact us block |  |  | 1
12.2.3 | CONTACT INFO in Footer | High (Required Immediately) | Need option to enable and disable Contact Info in footere from the Admin Control Panel ( Profile >> Profile List Page ) | Refer |  | 2
12.2.4 | Social Icon in Footer | High (Required Immediately) | Need option to enable and disable Contact us page from the Admin Control Panel ( Profile >> Profile List Page ) | Refer |  | 4
12.3 | Add Category Field for Vendor (Add New Table) | Medium | Requirement #11, the category added should be available in the Vendor Detailed Screen; Control from Admin Panel
12.4 | Vendor ID needs to be added in the vendor screen (Admin Panel only) | Medium | Vendor ID should be availble on the UI, currently it is in DB Table |  |  | 2
12.2.5 | Remove Lyklyst Branding | Low | Need option to enable and disable Lyklyst Branding from the Admin Control Panel |  |  | Please Explain
12.5 | Vendor Information | High (Required Immediately) | • Add GST No. • Add FSSAI (For Food FSSAI is mandatory) • EXIM Code In the footer of the vendor site | Refer |  | 2
13 | Vendor Packages | NA
14 | Disputes & Case / Support Tickets | NA |  |  |  | 8
14.1.1 | Return Orders | Medium | Need Enhancement to the Support ticket module in Customer Panel | Refer
14.1.2 | Complaints | Medium | Need Enhancement to the Support ticket module in Customer Panel | Refer
14.1.3 | Contacts | NA
15 | Sales | Medium |  |  |  | Need time to analyz after UI is freezed.
15.1 | Require Detailed Screen | Medium | Need a UI in Admin Panel - Design will shared later
16 | Product Page | Medium
16.1 | Product Page - Add Weight of the product | Medium
16.2 | Product Page - Add field HSN Code | Medium
16.3 | Product Page - Add Product Type field dropdown | Medium
16.4 | Product Page - Add Measurement (Enable Disable option should be available) | Medium
16.5 | Product Page - Tab for Shipping Cost Calculation | High (Required Immediately) | 1. Changes in product UI in Admin / Vendor Panel 2. Changes in Product Detail screen in Frotend ( Main and micro site) - (design will be provided later)
16.6 | Product Page - Tab for Estimated Delivery Date | High (Required Immediately) | 1. Changes in product UI in Admin / Vendor Panel 2. Changes in Product Detail screen in Frotend ( Main and micro site) - (design will be provided later)
16.7 | Product Page - Tab for Tax Calculation | High (Required Immediately) | 1. Changes in product UI in Admin / Vendor Panel 2. Changes in Product Detail screen in Frotend ( Main and micro site) - (design will be provided later)
17 | Reporting | Low
18 | FAQ Pages | Low
18.1 | Vendor FAQ | Low |  |  |  | 4
18.2 | Customer FAQ | Low |  |  |  | 2
19 | Order / Delivery Status Tracking & Notification | High (Required Immediately) | • New drop down should be add called ‘Tracking number’ • Add new field called estimated delivery date, the delivery date needs to be populated based on the shipping calendar • Mail should be sent out to the customer when the Delivery status is updated with status ‘on Delivery’ and Delivered with the tracking number |  |  | Need time to analyz after UI is freezed.
19.1 | Order Splitting / notifications | High (Required Immediately) | Order placed from main site (Sale from Multiple Vendor) The order placed from main site should be split and the sale code should be in the below format <Sale code>-<Vendor ID>-< Serial no> The Order number should start from 1* Series E.g. #102008309- 001-01 Order placed from micro site / partner site / Global site ( Sale from Single vendor) The number should start from 5* series E.g. #502008309 All the split invoices should be sent to customer by Email Vedor should see only his invoice not other vendors invoice |  |  | Need time to analyz after UI is freezed.
19.1.1 | Order placed from main site | High (Required Immediately) | Requirements mentioned above |  |  | Need time to analyz after UI is freezed.
19.1.2 | Mail Notification | High (Required Immediately) | Split Invoice should have Vendors Logo & Vendor Name (No Address need to be shown) Customer Information needs to be added Customer Delivery Address needs to be added Instruction Block needs to be added from Control Panel (Frontend Setting >> Email template) On the right hand corner it should show ‘Partnered with Lyklyst.com with Logo’ |  |  | Need time to analyz.
19.1.3 | Add Order Status (Cancelled) | High (Required Immediately) | Order Status dropdown = In Progress, On Hold & Cancelled Cancellation Reason = Text Expected Delivery Date / time = |  |  | Need time to analyz after UI is freezed.
19.2 | Mail when the Order status & Delivery Status are updated | High (Required Immediately) | Mail notification to Customers when the Order status & delivery status is updated |  |  | Need time to analyz
20 | Shipping Cost calculation | High (Required Immediately) | Create Separate Table for Shipping Cost Calculation and link it to product table Shipping cost = 100 (with in Bangalore) Shipping Cost = 150 ( Outside Bangalore) Shipping Cost = Free when order value is above 1500 |  |  | Need time to analyz
20.1 | Shipping Calendar / Expected Delivery Date | Medium |  |  |  | Need time to analyz
20.2 | Shipping Cost Calculation Based on the location | Medium |  |  |  | Need time to analyz
20.3 | Shipping Price Calculation & Status (API integration) | Medium |  |  |  | Need time to analyz
20.4 | Expected Delivery | High (Required Immediately) | Create Separate Table for Delivery Type and link it to product table 14 Working day from the date of order ( Maintain in Product Table) |  |  | Need time to analyz
21 | Packages for Vendors | NA | Duplicate of Requirement #13
22 | Improvements | Low
22.1 | Login using Social Media Facebook / Twitter | Low |  |  |  | 5
22.2 | Add Footer category in Main Site | NA
22.3 | Add Order number while raising the ticket | NA | Part of Requirement #14
22.4 | New UI – Main Site / Sub site & control Panel | NA
22.5 | Add Vendors name in the invoices | High (Required Immediately) | Need to add vendor name in the Email Notification |  |  | 2
22.6 | Invoice printing alignment | High (Required Immediately) | When we print the invoice from Control Panel the alingment is not correct |  |  | 3
22.7 | Vendor registration form let the * mark be there – for mandatory fields | High (Required Immediately) | Will provide the list later |  |  | 1
22.9 | Customer registration form let the * mark be there – for mandatory fields | High (Required Immediately) | Will provide the list later |  |  | 1
22.8.1 | Password conditions – caps,Number,symbol mandotory | low |  |  |  | 1
22.8.2 | State –drop down | Low |  |  |  | 1
22.8.3 | City – Drop down | Low |  |  |  | 1
22.8.4 | Valid format for pincode – for long term usage | Low |  |  |  | 1
22.9 | Email sending failed – | Low |  |  |  | 2
22.1 | After submitting – instead of message on the right side bottom corner, a new page with conformation is better | NA
22.11 | Selected items page – SM links to be shifted | Low | already done
22.12 | CLICK TO BUY option should also be given > Selected items page | Low | Need this option on the Card and it should go directly to Checkout page |  |  | 5
22.13 | And the order placed is not in order history | Low |  |  |  | 4
22.14 | Add one Image setting Thumb Nail (All Profile Page) | Low |  |  |  | Need time to analyz
22.15 | Ticket should be sent to Vendors by customer based on the order | NA | Part of Requirement #14
22.16 | Admin Panel Controls | Medium
22.16.1 | Redesign Admin Control Panel - Vendor | Medium |  |  |  | Need time to analyz
22.16.2 | Redesign Admin Control Panel - Customer | Medium |  |  |  | Need time to analyz
22.16.3 | Redesign Admin Control Panel - Admin | Medium |  |  |  | Need time to analyz
22.16.1 | Activate / Deactivate Profile from Admin Panel | Medium
22.16.2 | Activate / Deactivate Customer from Admin Panel | Medium
22.16.3 | Change reset Password for Profile in Admin Panel | Medium |  |  |  | 4
22.16.4 | Change reset Password for customer in Admin Panel | Medium |  |  |  | 2
22.17 | Assign package to Profile | Medium | Creating Package Module ( New UI - One Page) |  |  | Need time to analyz
22.19 | Admin Site footer link should be configurable | Low |  |  |  | 5
22.18 | Console Identify unused Graphics & Delete | Low | New UI to check unused images / photos Delete those images |  |  | 2
22.8 | Schedule a maintenance | High (Required Immediately) | When maintenance is scheduled need a page to be displayed automatically - Send Notification to site admin When the site is down need a page to be displayed automatically - send Notification to site admin
22.9 | Digitizing vendor onboarding | Medium | Need to Upload the Scanned documents and need to be available in vendor profile
22.1 | Terms & Conditions Recording in Control Panel | Medium | Need Vendor Onboarding Form & Separate form for vendor
22.11 | Product Bundle | Medium | Needs to be available for Vendors |  |  | 8
22.12 | Activation Payment >> Cash Payment activation | Medium | Need message for Dactivation on UI |  |  | 3

## Sheet1
2.2.
2.3
5.1
5.3
5.4
5.5
5.6
5.7
12.1
14.1.1 | 1 | Add Ticket Type field ( Dropdown)
14.1.2 |  | Complaints
feedback
Order Related ( Upon select enale Order Field)
Technical
Offers & Discounts
| Add new Field |  | Order Number | Dropdown on only his order - Date - Description
| Add New Field |  | Vendor Name | Automatically populated once the order is selected
| Add New Field |  | Status | Open
In Progress
Completed
When the Ticket is sent one copy should go to Vendor Paneland another to Admin Panel
Vendor should see only tickets assigned to him
Admin Should see all Vendor tickets
Vendor should be in a position to reply to customer
12.5
6
Add featured product block before related products

## Main
Mobile Application - Web app | Web application
https://github.com/gurayyarar/AdminBSBMaterialDesign
Ui Design for Control Panel - Admin / Login / | Use above Template and rearrange options
Ui Design for Control Panel - Customer | Use above Template and rearrange options
Ui Design for Control Panel - Vendor Login & Registration | Use above Template and rearrange options
Enhance Details Screen of Vendor | Build New UI, Add new fields / table & additional Controls
Enhance Details Screen of Product | Build New UI, Add new fields / table & additional Controls
Enhance Details Screen of Order | Build New UI, Add new fields / table & additional Controls
Tax Calculation | Build New UI, Add new fields / table & additional Controls
Shipping Date / Shipping Type / Tracking / API Integration | Build New UI, Add new fields / table, additional Controls & API integration ( 3 service provider's API)
Event Module | Build New UI, Add new fields / table & additional Controls
Package / Vendor Registartion Page | Enhance Package module (excisting); Require new UI on Vendor registartion page / new form for vendor registration; Vndor should be in a position subscribe package from the Vendor registration page
Tickets | Enhance UI, add Order ID & Created Date / vendor name / ; message should go to Vendor & Admin
Controls / Authorization | For Vendor Eg. Enable & Disable Page / blocks / features vendor UI & Control Panel ( from Admin Panel)